SPRINT REVIEW REPORT GROUP 05

Sprint 7: Final Delivery

Boot-Tracker: Lead Management and Payment System

Organization: Coding Bootcamps ESPOL

Project: Boot-Tracker Platform

Closing Date: en curso, corte al 12-ago-2026 (milestone objetivo: 11-ago-2026, ventana real hasta 19-ago-2026)

## Sprint Summary

This report is a status snapshot, not a closing document: Sprint 7 (6-19 ago 2026) is still running as of this cut. All six milestone-tagged closing tasks (final acceptance testing, deployment guide, client demo, individual contributions, final mobile builds, and the signed acceptance certificate) remain open in Linear, matching the real state: they depend on the client's final review and on each team member's own write-up, neither of which can be closed early. Alongside that closing scope, 21 client-driven issues have already closed in this sprint's window (6-ago onward): an analytics expansion, lead-lifecycle refinements, payment bug fixes, a responsive-design pass, data-integrity hardening, and initial groundwork for a WhatsApp bot integration.

## User Stories Covered

HST-025-adjacent: per-salesperson analytics and comparison tooling.

CR-004/CR-011 family continuation: lead lifecycle and duplicate/consent handling.

## Sprint Tasks (Linear)

| Issue | Description | Assignee | Status |
| --- | --- | --- | --- |
| CB-78 | S7-1 - Scrum: cierre del proyecto + acta de aceptacion Dra. Vaca | Jose Chong | Backlog |
| CB-79 | S7-2 - DevOps: guia de despliegue + entrega final al cliente | Juan Munizaga | Backlog |
| CB-80 | S7-3 - QA: testing de aceptacion final + reporte HST | Zahid Diaz | Backlog |
| CB-81 | S7-4 - Frontend: demo final web + grabacion del sistema | Gabriela Jimenez | Backlog |
| CB-82 | S7-5 - Docs: contribuciones individuales + actualizacion documento final | Annabella Sanchez | Backlog |
| CB-83 | S7-6 - Mobile: builds finales iOS/Android + entrega | Isabella Martin | Backlog |

## Additional Client-Driven Scope Delivered This Sprint

Beyond the planned milestone scope, the following work was delivered in response to live client feedback and usability findings during this sprint window. Each item is a real, closed Linear issue; grouped here by theme for readability. Full per-issue detail: SCRUM_Evidence/Sprint_7/github_issues_s7.md and the Linear workspace.

| Theme | Description | Status |
| --- | --- | --- |
| Analytics expansion (3 issues) | Per-salesperson metrics filtered by date range (CB-198), salesperson-comparison tab (CB-194), program/cohort columns with filtering on the Users screen (CB-195). | Done |
| Lead lifecycle refinement (5 issues) | Terminal Discarded status with a mandatory reason (CB-191), each interaction now snapshots the lead's status at that moment (CB-192), assigned-since timestamp shown on the lead card (CB-190), bulk bootcamper distribution to Finance with select-all (CB-193), mandatory data-usage consent at bootcamper account creation (CB-196). | Done |
| Payments/notifications bug fixes (4 issues) | Finance can see the receipt image, not just OCR fields, when reviewing (CB-189), coordinator email now states its origin (CB-188), coordinator email linked to a reachable URL (CB-187), 500 error on receipt upload fixed (CB-186). | Done |
| Responsive / UX polish (3 issues) | Responsive receipt-upload and account-activation flow for the bootcamper (CB-199), responsive account activation, session-expiry and password-recovery screens (CB-203), scroll-bounce background fix (CB-204). | Done |
| Data-integrity hardening (3 issues) | Block lead creation with a staff member's email (CB-200), allow re-enrollment into a program already completed under a different cohort (CB-201), assign/change a bootcamper's cohort from the Users screen (CB-202). | Done |
| WhatsApp bot groundwork (3 issues) | Shared-secret authentication for the bot (CB-173), phone-number normalization to match leads to a WhatsApp identifier (CB-172), query/create/update lead endpoints for the bot (CB-174). Follows the integration plan researched in Sprint 4 (CB-84). | Done |

## Pending / Carried Over

| Issue | Description | Assignee | Status |
| --- | --- | --- | --- |
| CB-78 | S7-1 - Scrum: cierre del proyecto + acta de aceptacion Dra. Vaca | Jose Chong | Backlog |
| CB-79 | S7-2 - DevOps: guia de despliegue + entrega final al cliente | Juan Munizaga | Backlog |
| CB-80 | S7-3 - QA: testing de aceptacion final + reporte HST | Zahid Diaz | Backlog |
| CB-81 | S7-4 - Frontend: demo final web + grabacion del sistema | Gabriela Jimenez | Backlog |
| CB-82 | S7-5 - Docs: contribuciones individuales + actualizacion documento final | Annabella Sanchez | Backlog |
| CB-83 | S7-6 - Mobile: builds finales iOS/Android + entrega | Isabella Martin | Backlog |

## Team

| Role | Member |
| --- | --- |
| Scrum Master | Jose Chong (Jlchong3) |
| Backend | Juan Munizaga, Zahid Diaz, Jose Chong |
| Frontend | Gabriela Jimenez, Annabella Sanchez |
| Mobile | Isabella Martin |

## Review Notes

None of the six core S7 issues were altered during this audit: unlike the S4-S6 findings, these are legitimately pending: they require the client's signed acceptance, the live final demo recording, and each team member's own contributions paragraph, none of which exist yet as of 12-ago-2026.

The WhatsApp bot groundwork (CB-172/173/174) is new scope not previously documented anywhere in the project's SCRUM evidence or the final report draft; flagged here so it is not lost before the final report is closed.

________________________________________

Customer Conformity and Acceptance

PhD. Carmen Vaca

Director of Coding Bootcamps ESPOL

[ % PENDIENTE-FIRMA — se completa cuando la clienta firme la revision ]